## LEGEND
C1 — Construction Documentation Intelligence Platform
Document Taxonomy v0.4 ¦ FIDIC Red Book 1999 & 2017 ¦ GCC Market
DESIGN PRINCIPLE
Taxonomy = document types only | The taxonomy defines WHAT a document is. Everything else — who issued it, who received it, date, reference number, contract it belongs to, party role of the issuer — is metadata extracted automatically by the ingestion pipeline. No 'Issued By' column exists in the taxonomy. The AI infers party relationships from the contracts loaded into the database.
TIER CLASSIFICATION
Tier 1 — Critical | Directly affects money, time, liability, or contractual enforceability. Can create or defend a position in arbitration or court.
Tier 2 — Important | Used for control, monitoring, planning, justification, or analysis. Essential context for governance, audit, and BI.
Tier 3 — Supporting | Execution evidence, technical detail, logs, and registers. Background documentation supporting Tier 1 and Tier 2.
METADATA EXTRACTED AT INGESTION (not in taxonomy)
Document Reference Number | Extracted from document header
Document Date | Extracted from document header
Issuing Party | Extracted from document — matched to Party Register
Receiving Party | Extracted from document — matched to Party Register
Contract Reference | Extracted and linked to contract in DB
Project Name | Extracted and linked to project record
FIDIC Sub-Clause Reference | Extracted where present — validated against edition
Document Status | EXECUTED / DRAFT / SUPERSEDED / DISPUTED / PENDING / REJECTED / EXPIRED
Language | EN / AR / EN-AR / EN-AR-CONFLICT
Revision Number | Extracted from document title block
Contractual Time-Bar Deadline | Calculated — issue date + notice period per contract clause
FIDIC EDITION CLAUSE MAPPING (key changes 1999 → 2017)
8.4 [1999] → 8.5 [2017] | Extension of Time. New 8.4 in 2017 = Advance Warning.
3.5 [1999] → 3.7 [2017] | Engineer's Agreement or Determination.
2.5 [1999] → Cl. 20 [2017] | Employer's Claims moved into Clause 20 alongside Contractor's Claims.
20.1 [1999] → 20.2.1 [2017] | Notice of Claim — now covers both parties symmetrically.
20.4 [1999] → 21.4 [2017] | DAB renamed DAAB (Dispute Avoidance/Adjudication Board).
Cl. 19 [1999] → Cl. 18 [2017] | Force Majeure renamed Exceptional Events. Clauses 18 and 19 swapped.
PARTY ROLE LOGIC
AI-inferred mapping | The taxonomy uses FIDIC contractual roles throughout (Employer / Engineer / Contractor). The actual company filling each role is inferred by the AI from the contracts in the DB. See PARTY REGISTER sheet for all roles and delivery model mapping.
Subcontractors | Do not have separate document types in the taxonomy. Their existence, scope, and relationship to the Main Contractor is inferred by the AI from the Subcontracts loaded into the DB.

## PARTY REGISTER
Party Role | Delivery Model(s) | Description | Reports To (Contractually) | Typical Contract / Appointment
Employer | All models | Project owner and ultimate decision-maker. Holds all contracts. Provides site, funding, and Employer's Requirements. | Board / Investors / Sovereign Authority | None — is the contracting authority
PMC (Project Management Consultant) | Traditional; Design & Build; Construction Management | Manages full project delivery on behalf of Employer. Coordinates all consultants and contractors. On many GCC projects formally appointed as the FIDIC Engineer. | Employer | Consultancy / Professional Services Agreement
Design Consultant | Traditional; Design & Build (pre-novation); EPC (Employer-retained for ER preparation) | Provides architectural and / or engineering design. In Traditional delivery, retained by Employer throughout. In D&B, often novated to the Contractor after award. | Employer (traditional) / Contractor (post-novation in D&B) | Consultancy Agreement (or Novation Agreement post-award)
Supervision Consultant | Traditional; Design & Build; EPC (where Employer appoints independent supervisor) | Independent site supervision. Witnesses tests, reviews submittals, issues NCRs and Inspection Reports. Often formally appointed as the FIDIC Engineer or acts under the PMC. | PMC (if PMC holds Engineer role) / Employer (if directly appointed) | Consultancy Agreement
Cost Consultant / Quantity Surveyor (QS) | All models — may be integrated into PMC or a separate appointment | Prepares and prices the BOQ; measures work in progress; recommends IPC valuations; prepares Cost Reports. May act as the commercial arm of the PMC or as a standalone appointment. | PMC / Employer | Consultancy Agreement (standalone) or scope within PMC Agreement
Engineer (FIDIC Contractual Role) | All models — FIDIC-based contracts | The contractual role defined by FIDIC. Issues instructions, certifies payments, makes determinations, issues TOC and Performance Certificate. Must act impartially. In practice filled by PMC, Supervision Consultant, or a dedicated firm. The AI infers which party fills this role from the contracts in the DB. | Employer (contractually bound to act impartially) | Defined in the Contract Agreement — not a separate appointment
Main Contractor | Traditional; Design & Build | Holds the main construction contract directly with the Employer. Responsible for the full scope under a single contract. Appoints domestic subcontractors; may have nominated subcontractors imposed by the Employer. | Engineer (contractually); Employer (commercially) | Main Contract (FIDIC Red / Yellow / Silver Book or bespoke)
Package Contractor | Construction Management; multi-package Traditional | Holds a direct contract with the Employer for a defined work package. Parallel to — not under — other Package Contractors. Interface Agreements govern interactions between packages. | Engineer (contractually); Employer (commercially) | Package Contract (FIDIC-based or bespoke)
Nominated Subcontractor | Traditional; Design & Build (where Employer nominates specific subcontractors) | Selected by the Employer and nominated to the Main Contractor under FIDIC Clause 5. Triangular liability: Employer (selection) / Contractor (management) / Nominated Sub (execution). AI infers existence and scope from Subcontract in DB. | Main Contractor (contractually); Employer (selection authority) | Subcontract (back-to-back with main contract provisions)
Domestic Subcontractor | All models | Selected and appointed by the Main Contractor or Package Contractor. No direct contractual relationship with the Employer. AI infers existence and scope from Subcontract in DB. | Main Contractor / Package Contractor | Subcontract (Contractor's standard form)
Independent Expert | All models — invoked in dispute / forensic contexts | Appointed for dispute resolution, expert determination, or forensic analysis. Acts independently of all parties. May be appointed jointly or by an appointing authority (ICC, DIAC, CIArb, RICS). | Appointing authority / Court / Tribunal | Expert Appointment Letter
DAB / DAAB | All models — FIDIC-based contracts | Dispute Adjudication / Avoidance Board. Independent panel under FIDIC Clause 20 [1999] / Clause 21 [2017]. Issues binding decisions. Renamed DAAB in 2017 with enhanced avoidance role. | Independent — appointed under tripartite DAB/DAAB Agreement | DAB / DAAB Agreement (tripartite: Employer + Contractor + Board)
Lender / Funder | All models — where project finance is involved | Provides debt or equity finance. May appoint an independent Lender's Technical Advisor (LTA) to monitor construction and certify drawdown conditions. May require step-in rights and direct agreements with contractors. | Own governance / Investment committee | Finance Agreement / Loan Agreement / Facility Agreement
Government Authority | All models — jurisdiction-specific | Issues statutory permits, NOCs, completion and occupation certificates. The specific authority, permit type, and process is jurisdiction-specific and handled through the Reference Document library, not the taxonomy. | Relevant Ministry / Department / Municipality | Statutory — no contract. Governed by applicable law.
Third Party — Bank / Surety | All models | Issues financial guarantees on behalf of the Contractor: Performance Bond, Advance Payment Guarantee, Retention Bond, Parent Company Guarantee. | Own governance | Bank Facility Agreement / Counter-Indemnity
Third Party — Insurer | All models | Issues insurance policies. Key classes: CAR (Contractor's All Risks); TPL (Third Party Liability); PI (Professional Indemnity — for consultants); Decennial Liability (mandatory in UAE and increasingly in Saudi Arabia). | Own governance / Regulatory authority | Insurance Policy
Third Party — Testing Laboratory | All models | Independent accredited laboratory conducting material tests, soil investigations, and specialist testing. Independence from the Contractor is critical for forensic credibility. | Own governance (accredited by relevant authority) | Testing Services Agreement

## Governance
No. | Document | Possible Formats | Tier
1 | Project Charter | PDF, DOCX | Tier 2
2 | Governance Framework | PDF, DOCX | Tier 2
3 | Delegation of Authority (DOA) | PDF, DOCX, XLSX | Tier 2
4 | Approval Matrix | PDF, XLSX | Tier 2
5 | Organisation Chart | PDF | Tier 3
6 | Committee / Steering Meeting Minutes | PDF, DOCX | Tier 2
7 | Executive / Board Reports | PDF, PPTX, DOCX | Tier 1
8 | Stage Gate Approvals | PDF, DOCX | Tier 1
9 | Budget Approval | PDF, DOCX | Tier 1
10 | Funding Approval | PDF, DOCX | Tier 1
11 | Policies | PDF, DOCX | Tier 2
12 | Procedures | PDF, DOCX | Tier 2
13 | Audit Plan | PDF, DOCX | Tier 2
14 | Audit Report | PDF, DOCX | Tier 1
15 | Investigation Report | PDF, DOCX | Tier 1
16 | Compliance Report | PDF, DOCX | Tier 1

## Legal_Contractual
No. | Document | Possible Formats | Tier
1 | Contract Agreement (Main Contract) | PDF | Tier 1
2 | Contract Agreement (Consultant Appointment) | PDF | Tier 1
3 | Contract Agreement (Package Contract) | PDF | Tier 1
4 | Interface Agreement | PDF | Tier 1
5 | Letter of Acceptance / Award (LOA) | PDF | Tier 1
6 | Letter of Intent (LOI) | PDF | Tier 1
7 | Letter of Tender | PDF | Tier 1
8 | General Conditions (FIDIC) | PDF | Tier 2
9 | Particular Conditions | PDF, DOCX | Tier 1
10 | Contract Data / Appendix to Tender | PDF, DOCX | Tier 1
11 | Employer's Requirements | PDF, DOCX | Tier 1
12 | Contractor's Proposal | PDF, DOCX | Tier 1
13 | Addenda (Pre-Contract) | PDF, DOCX | Tier 2
14 | Tender Clarifications | PDF, DOCX | Tier 2
15 | Performance Bond | PDF | Tier 1
16 | Advance Payment Guarantee | PDF | Tier 1
17 | Retention Bond | PDF | Tier 1
18 | Parent Company Guarantee | PDF | Tier 1
19 | Insurance Policies (CAR, TPL, PI, Decennial) | PDF | Tier 1
20 | Contractual Notices (General) | PDF, DOCX | Tier 1
21 | Engineer's Instructions | PDF, DOCX | Tier 1
22 | Engineer's Determinations (FIDIC 3.7 [2017] / 3.5 [1999]) | PDF, DOCX | Tier 1
23 | Contract Amendments / Addenda (Post-Contract) | PDF | Tier 1
24 | Side Letters | PDF | Tier 1
25 | Novation Agreement | PDF | Tier 1
26 | Collateral Warranty | PDF | Tier 1
27 | Settlement Agreement / Deed | PDF | Tier 1
28 | Dispute Notice / Notice of Dissatisfaction (NOD) | PDF, DOCX | Tier 1

## Commercial
No. | Document | Possible Formats | Tier
1 | Bill of Quantities (BOQ) | PDF, XLSX | Tier 1
2 | Schedule of Prices / Rates | PDF, XLSX | Tier 1
3 | Cost Breakdown Structure (CBS) | PDF, XLSX | Tier 2
4 | Payment Application / Contractor's Statement | PDF, XLSX | Tier 1
5 | Interim Payment Certificate (IPC) (FIDIC 14.6) | PDF | Tier 1
6 | Invoice | PDF | Tier 2
7 | Payment Record / Remittance Advice | PDF, XLSX | Tier 1
8 | Final Statement (Contractor's) | PDF, XLSX | Tier 1
9 | Final Account | PDF, XLSX | Tier 1
10 | Final Payment Certificate (FIDIC 14.13) | PDF | Tier 1
11 | Variation Proposal / Contractor's Quotation | PDF, DOCX, XLSX | Tier 1
12 | Variation Order (VO) (FIDIC Clause 13) | PDF, DOCX | Tier 1
13 | Daywork Sheets | PDF, XLSX | Tier 2
14 | Measurement Sheets | PDF, XLSX | Tier 2
15 | Cash Flow Forecast | PDF, XLSX | Tier 2
16 | Cost Report | PDF, XLSX, PPTX | Tier 1
17 | Project Budget | PDF, XLSX | Tier 1
18 | Liquidated Damages Notice & Calculation (FIDIC 8.7/8.8) | PDF, DOCX | Tier 1

## PM_Controls
No. | Document | Possible Formats | Tier
1 | Business Case | PDF, DOCX, PPTX | Tier 2
2 | Feasibility Study | PDF, DOCX | Tier 2
3 | Project Management Plan (PMP) | PDF, DOCX | Tier 2
4 | Work Breakdown Structure (WBS) | PDF, XLSX | Tier 2
5 | Baseline Programme (FIDIC 8.3) | PDF, XER, MPP | Tier 1
6 | Revised Programme | PDF, XER, MPP | Tier 1
7 | Recovery Programme | PDF, XER, MPP | Tier 1
8 | Master Programme (Programme-wide) | PDF, XER, MPP | Tier 1
9 | Look-Ahead Schedule (3 / 6-week) | PDF, XLSX, XER | Tier 2
10 | As-Built Programme | PDF, XER, MPP | Tier 1
11 | Cost Baseline | PDF, XLSX | Tier 2
12 | Risk Management Plan | PDF, DOCX | Tier 2
13 | Risk Register | PDF, XLSX | Tier 1
14 | Quality Management Plan | PDF, DOCX | Tier 2
15 | HSE Plan | PDF, DOCX | Tier 2
16 | Procurement Plan | PDF, DOCX | Tier 2
17 | Communication Plan | PDF, DOCX | Tier 3
18 | Interface Management Plan | PDF, DOCX | Tier 2
19 | Monthly Progress Report | PDF, DOCX, PPTX | Tier 1
20 | KPI Reports | PDF, XLSX, PPTX | Tier 1
21 | Earned Value Report | PDF, XLSX | Tier 1
22 | Issue Log | PDF, XLSX | Tier 2
23 | Change Log / Variation Register | PDF, XLSX | Tier 2
24 | Lessons Learned Report | PDF, DOCX | Tier 3

## Engineering
No. | Document | Possible Formats | Tier
1 | Design Basis Report | PDF, DOCX | Tier 1
2 | Design Criteria | PDF, DOCX | Tier 2
3 | Calculations | PDF, DOCX, XLSX | Tier 2
4 | Drawings — Issued for Construction (IFC) | PDF, DWG, DXF, RVT | Tier 2
5 | Specifications | PDF, DOCX | Tier 2
6 | Shop Drawings / Submittals | PDF, DWG, DXF | Tier 2
7 | Technical Reports | PDF, DOCX | Tier 1
8 | BIM Models / BIM Execution Plan | RVT, IFC, NWD, PDF | Tier 2
9 | Clash Reports | PDF, NWD | Tier 2
10 | Value Engineering Reports | PDF, DOCX | Tier 1
11 | Design Review Reports | PDF, DOCX | Tier 1
12 | Design Change Notices (DCN) | PDF, DOCX | Tier 1
13 | Request for Information (RFI) | PDF, DOCX | Tier 1
14 | Response to RFI | PDF, DOCX | Tier 1

## Procurement
No. | Document | Possible Formats | Tier
1 | Procurement Plan | PDF, DOCX | Tier 2
2 | Vendor Prequalification Records | PDF, DOCX, XLSX | Tier 2
3 | Tender Documents (Sub-packages) | PDF, DOCX | Tier 2
4 | Bid Evaluation Reports | PDF, DOCX, XLSX | Tier 1
5 | Purchase Orders | PDF, DOCX | Tier 2
6 | Subcontracts | PDF | Tier 1
7 | Vendor / Shop Drawings | PDF, DWG | Tier 2
8 | Vendor Datasheets / Product Data Sheets | PDF | Tier 2
9 | Factory Acceptance Test (FAT) Reports | PDF | Tier 2
10 | Material Certificates / Mill Certificates | PDF | Tier 1
11 | Delivery Notes / Waybills | PDF | Tier 2
12 | Shipping / Import Documents | PDF | Tier 2

## Construction
No. | Document | Possible Formats | Tier
1 | Method Statements | PDF, DOCX | Tier 2
2 | Temporary Works Design | PDF, DWG | Tier 2
3 | Work Permits / Permit to Work (PTW) | PDF, DOCX | Tier 2
4 | Site Instructions (SI) | PDF, DOCX | Tier 1
5 | Daily Site Reports | PDF, DOCX | Tier 1
6 | Site Diaries / Engineer's Diary | PDF, DOCX | Tier 1
7 | Progress Photographs | JPG, PDF | Tier 2
8 | Resource Reports (Labour & Plant) | PDF, XLSX | Tier 1
9 | Equipment Utilisation Reports | PDF, XLSX | Tier 2
10 | Field Change Requests | PDF, DOCX | Tier 2
11 | Survey / Setting Out Records | PDF, DWG, XLSX | Tier 1
12 | Meeting Minutes (Progress / Technical / Commercial) | PDF, DOCX | Tier 1
13 | Early Warning Notices | PDF, DOCX | Tier 1
14 | Suspension Notice — by Engineer (FIDIC 8.8) | PDF, DOCX | Tier 1
15 | Suspension Notice — by Contractor (FIDIC 16.1) | PDF, DOCX | Tier 1
16 | Termination Notice — by Employer (FIDIC 15.2) | PDF, DOCX | Tier 1
17 | Termination Notice — by Contractor (FIDIC 16.2) | PDF, DOCX | Tier 1
18 | Force Majeure / Exceptional Event Notice (FIDIC Cl. 18 [2017] / 19 [1999]) | PDF, DOCX | Tier 1
19 | Acceleration Instruction / Agreement | PDF, DOCX | Tier 1

## Quality_HSE
No. | Document | Possible Formats | Tier
1 | Project Quality Plan (PQP) | PDF, DOCX | Tier 2
2 | Inspection & Test Plans (ITP) | PDF, DOCX, XLSX | Tier 2
3 | Material Inspection Requests (MIR) | PDF, DOCX | Tier 2
4 | Work Inspection Requests (WIR) | PDF, DOCX | Tier 2
5 | Inspection Reports | PDF, DOCX | Tier 1
6 | Test Reports | PDF, DOCX, XLSX | Tier 1
7 | Non-Conformance Reports (NCR) | PDF, DOCX | Tier 1
8 | Corrective Action Reports (CAR) | PDF, DOCX | Tier 1
9 | Preventive Action Reports (PAR) | PDF, DOCX | Tier 2
10 | Safety Reports (Weekly / Monthly) | PDF, DOCX | Tier 1
11 | Incident / Accident Reports | PDF, DOCX | Tier 1
12 | Environmental Reports | PDF, DOCX | Tier 1

## Claims_Disputes
No. | Document | Possible Formats | Tier
1 | Notice of Claim (FIDIC 20.2.1 [2017] / 20.1 [1999]) | PDF, DOCX | Tier 1
2 | Notice of Delay (FIDIC 8.5 [2017] / 8.4 [1999]) | PDF, DOCX | Tier 1
3 | Extension of Time (EOT) Claim | PDF, DOCX | Tier 1
4 | Prolongation / Additional Cost Claim | PDF, DOCX, XLSX | Tier 1
5 | Disruption Claim | PDF, DOCX, XLSX | Tier 1
6 | Acceleration Claim | PDF, DOCX, XLSX | Tier 1
7 | Employer's Claim (FIDIC 2.5 [1999] / 20.2 [2017]) | PDF, DOCX | Tier 1
8 | Delay Analysis Report | PDF, DOCX, XER | Tier 1
9 | Expert Reports (Delay / Quantum / Technical) | PDF, DOCX | Tier 1
10 | Engineer's Determination (FIDIC 3.7 [2017] / 3.5 [1999]) | PDF, DOCX | Tier 1
11 | Notice of Dissatisfaction (NOD) | PDF, DOCX | Tier 1
12 | DAB / DAAB Decision (FIDIC 21.4 [2017] / 20.4 [1999]) | PDF, DOCX | Tier 1
13 | Arbitration Notice / Request for Arbitration | PDF, DOCX | Tier 1
14 | Claim Settlement / Settlement Deed | PDF | Tier 1

## Testing_Handover
No. | Document | Possible Formats | Tier
1 | Testing Procedures | PDF, DOCX | Tier 2
2 | Pre-Commissioning Reports | PDF, DOCX, XLSX | Tier 1
3 | Commissioning Reports / Tests on Completion (FIDIC Cl. 9) | PDF, DOCX, XLSX | Tier 1
4 | Performance Test Reports | PDF, DOCX, XLSX | Tier 1
5 | Reliability Test Reports | PDF, DOCX | Tier 1
6 | System Completion Certificates | PDF | Tier 1
7 | Taking-Over Request — Contractor's Application | PDF, DOCX | Tier 2
8 | Taking-Over Certificate (FIDIC 10.1) | PDF | Tier 1
9 | Snagging / Punch List | PDF, XLSX | Tier 2
10 | Defects Notification & Rectification Notice (FIDIC Cl. 11) | PDF, DOCX | Tier 1
11 | As-Built Drawings | PDF, DWG, RVT | Tier 2
12 | O&M Manuals | PDF, DOCX | Tier 2
13 | Training Records | PDF, DOCX | Tier 3
14 | Asset Register | PDF, XLSX | Tier 2
15 | Warranties & Guarantees (Equipment / Works) | PDF | Tier 1
16 | Final Payment Certificate (FIDIC 14.13) | PDF | Tier 1
17 | Performance / Defects Certificate (FIDIC 11.9) | PDF | Tier 1
18 | Handover Certificate (Operational) | PDF | Tier 1
19 | Authority Completion / Occupation Certificate | PDF | Tier 1